## WBC
This tracker outlines all tasks for Phase 3 of the MITRE challenge, covering development, execution, and documentation of DelphiQ’s quantum microinsurance solution. Key components include: QRU+FNO hybrid model for climate risk prediction QAOA optimization for payout allocation Parametric insurance logic for dynamic pricing Tasks span simulation, code integration, analysis, and documentation, aligned with Phase 3 deliverables. Team roles are assigned based on expertise, but assignments are flexible and open to reassignment. All tasks support reproducibility, quantum advantage assessment, and real-world relevance—culminating in a complete submission package with code, results, and write-up.
Task Description | Category | Priority | Assigned to | Status | Progress Notes | Comments | Blocker(s) if any | Due Date
Finalize QRU model and FNO architecture | Model Development | High | Sabari & Léa | Not Started |  |  |  | 2020-06-01
Integrate FNO with QRU circuit encoding | Integration | High | Sabari & Léa | Not Started |  |  |  | 2024-06-01
Implement QAOA layer for regional CVaR optimization | Optimization | High | Sabari & Léa | Not Started |  |  |  | 2026-06-01
Connect QRU outputs to QAOA input pipeline | Integration | High | Sabari & Léa | Not Started |  |  |  | 2026-06-01
Run simulations on qBraid (CPU & QPU) | Execution | High | Sabari & Léa | Not Started |  |  |  | 2028-06-01
Design parametric insurance rules engine | Logic Design | High | Nico & Jacinta | Not Started |  |  |  | 2020-06-01
Define input schema from QRU+QAOA | Integration | High | Nico & Jacinta | Not Started |  |  |  | 2022-06-01
Implement dynamic pricing for microinsurance | Algorithm Dev | High | Nico & Jacinta | Not Started |  |  |  | 2024-06-01
Workflow diagram & system architecture | Documentation | High | All | Not Started |  |  |  | 2020-06-01
End-to-end code pipeline (modular) | Codebase | High | All | Not Started |  |  |  | 2028-06-01
Parametric logic design + test cases | Testing | High | All | Not Started |  |  |  | 2020-06-01
Parametric insurance layer integration | Integration | High | All | Not Started |  |  |  | 2028-06-01
Final write-up + citations | Documentation | High | All (compiled by Jacinta) | Not Started |  |  |  | 2005-07-01
Zip submission: DelphiQ_ClimateRisk_Phase3.zip | Submission | High | Jacinta | Not Started |  |  |  | 2006-07-01
Execute finalized model on qBraid (risk heat maps & forecast metrics) | Solution Execution | High | Sabari & Léa | Not Started |  |  |  | 1930-06-01
Generate premium pricing outputs & payout calculations | Solution Execution | High | Nico & Jacinta | Not Started |  |  |  | 1930-06-01
Quantitative evaluation vs classical baselines | Analysis | High | All | Not Started |  |  |  | 2002-07-01
Draft societal & market impact analysis | Impact Analysis | High | All | Not Started |  |  |  | 2004-07-01
Ensure reproducibility & judge-ready scripts on qBraid | Reproducibility | High | All | Not Started |  |  |  | 2005-07-01
Maintain code & environment config (qbraid.yaml) | Maintenance | Low | Sabari & Léa | Not Started |  |  |  | 2003-07-01
Contribute dashboard payout simulation interface | Dashboard UI | Low | Nico & Jacinta | Not Started |  |  |  | 2003-07-01
README.md (setup, usage, qBraid) | Documentation | Low | All | Not Started |  |  |  | 2003-07-01
Setup qBraid environment & allocate credits | Platform Setup | Low | All | Not Started |  |  |  | 2015-06-01
Document model accuracy, fidelity, and performance | Documentation | Medium | Sabari & Léa | Not Started |  |  |  | 2003-07-01
Export rainfall forecasts, CVaR maps, payout decisions | Export/Output | Medium | Sabari & Léa | Not Started |  |  |  | 2003-07-01
Connect CelsiusPro API / simulate payout | Simulation/API | Medium | Nico & Jacinta | Not Started |  |  |  | 2026-06-01
Model stakeholder outcomes | Impact Analysis | Medium | Nico & Jacinta | Not Started |  |  |  | 2028-06-01
Generate premium, payout fairness, loss data | Output Generation | Medium | Nico & Jacinta | Not Started |  |  |  | 2003-07-01
Draft market impact & feasibility write-up | Documentation | Medium | Nico & Jacinta | Not Started |  |  |  | 2005-07-01
Benchmark plots & performance graphs | Visualization | Medium | All | Not Started |  |  |  | 2003-07-01
Run portfolio diversification & reinsurance optimization | Evaluation | Medium | Sabari & Léa | Not Started |  |  |  | 2001-07-01
Document toolchain integration & technical transparency | Documentation | Medium | All | Not Started |  |  |  | 2025-06-01
Document execution trade-offs & mitigation strategies | Documentation | Medium | All | Not Started |  |  |  | 2003-07-01

## MITRE
This task tracker outlines the full set of actionable items required to implement and deliver the final submission for Phase 3 of the MITRE Quantum Chemistry Infrastructure Challenge. The tasks span the entire pipeline—from molecular selection and Hamiltonian simulation to result analysis, benchmarking, reproducibility, and report generation—ensuring alignment with the official Phase 3 deliverables and judging criteria. The tasks are categorized by description, category (technical, documentation, benchmarking, etc.), and mapped to the relevant frameworks and execution platforms (e.g., Tangelo, Qiskit, PySCF, qBraid). Progress fields and blockers are also included to facilitate team coordination. Note: Initial task assignments were made randomly to help distribute the workload. Team members are encouraged to review and adjust assignments based on expertise and availability.
Task Description | Category | Priority | Assigned to | Status | Progress Notes | Comments | Blocker(s) if any | Due Date
Select representative asphalt molecule (Phenanthrene) for degradation study | Chemistry | High | Sabari | To Do |  |  | None | 2025-06-20
Optimize geometry using DFT on classical workstation | Preprocessing | High | Sabari | To Do |  |  | None | 2025-06-21
Compute 1-/2-electron integrals using chosen basis set | Quantum Chemistry | High | Sabari | To Do |  |  | None | 2025-06-22
Reduce Hamiltonian dimension using DMET or CASSCF active space | Quantum Chemistry | High | Sabari | To Do |  |  | None | 2025-06-23
Map reduced fermionic Hamiltonian to qubits using JW/BK | Encoding | High | Sabari | To Do |  |  | None | 2025-06-24
Choose and configure QITE/QPE circuits | Quantum Simulation | High | Jacinta | To Do |  |  | None | 2025-06-25
Compile circuits with qubit topology and noise-aware transpiler | Quantum Simulation | High | Jacinta | To Do |  |  | None | 2025-06-26
Run circuits on qBraid HPC/QPU | Execution | High | Jacinta | To Do |  |  | Access pending | 2025-06-27
Extract oxidation energy, convergence plots, trends | Results | High | Jacinta | To Do |  |  | None | 2025-06-28
Instructions for qBraid execution, inputs, expected outputs | Documentation | High | Léa | To Do |  |  | None | 2025-07-02
Main report summarizing methods, results, impact | Documentation | High | Jacinta | To Do |  |  | None | 2025-07-03
Zip writeup, figures, results, code | Packaging | High | Jacinta | To Do |  |  | None | 2025-07-05
Upload final package with required format | Submission | High | Jacinta | To Do |  |  | None | 2025-07-06
Compare oxidation energies and reactivity with DFT baseline | Benchmarking | Medium | Sabari | To Do |  |  | None | 2025-06-29
Highlight benefits over classical (correlation, scaling) | Benchmarking | Medium | Jacinta | To Do |  |  | None | 2025-06-30
Include annotated circuit visualizations | Documentation | Medium | Lea | To Do |  |  | None | 2025-07-01
Push code with tags and instructions | DevOps | Medium | Léa | To Do |  |  | None | 2025-07-02